## Slide 1
Around the Horn:
How the UF Successfully
Fielded a Team
that Integrates
Health Science and University Libraries

## Slide 2
Brian W. Keith
Associate Dean, Administration and Faculty Affairs,
George A. Smathers Libraries
Cecilia Botero
Associate Dean of the George A. Smathers Libraries and
Director of the Health Science Center Libraries
Michele R. Tennant
Assistant Director, Biomedical and Health Information Services,
Health Science Center Libraries
Bioinformatics Librarian, UF Genetics Institute

## Slide 3
ufdc.ufl.edu/AA00011332

## Slide 4
Our presentation will cover
the 2009 integration of the UF Health Sciences Center Libraries and the George A. Smathers Libraries (main campus system)
    a. planning
    b. systems
    c. outcomes
results and lessons learned

## Slide 5: Background
UF library system as of 2008 consisted of 3 systems:
Lawton Chiles Legal Information Center (LIC)

## Slide 6: Background
UF library system as of 2008 consisted of 3 systems:
Lawton Chiles Legal Information Center
Health Sciences Center Libraries (HSCL)
  Health Science Center (Gainesville)
  Borland branch library (Jacksonville)
  Veterinary Medicine Reading Room (Gainesville)

## Slide 7: Background
UF library system as of 2008 consisted of 3 systems:
Lawton Chiles Legal Information Center
Health Sciences Center Libraries
George A. Smathers Libraries (Smathers)
  Special and Area Studies Collections
  Government Documents and Maps
  Humanities and Social Sciences Library
  Marston Science Library
  Departmental Branches
    Architecture and Fine Arts
    Education
    Journalism
    Music

## Slide 8: Background
Historically, there was extensive collaboration between the Smathers Libraries and HSCL, particularly in the areas of:
  the acquisition of library resources,
  Tenure & Promotion, and
  Library Management System

## Slide 9: Integration Planning
Fall 2008, the HSCL and Smathers Libraries were advised that the President had decided to integrate the 2 systems as soon as feasible.
Negotiated an implementation of July 1, 2009.

## Slide 10: Integration Planning
October 2008, Dean and HSCL Director agreed to work on an integration proposal to jointly submit to the Provost that would allow the HSCL retain autonomy in regard to servicing its customers’ needs.

## Slide 11: Integration Planning
On January 21, 2009, employees of the Smathers and HSCL libraries were enlisted to Integration working groups:
  Administrative Services (Human Resources and Financial Services)
  Access Support (ILL, Circulation, Library-Wide Policies)
  Budget Preparation
  Development (Grants, PR)
  Digital Services/Institutional Repositories
  Facilities
  Public Services/Collections Management
  Systems
  Technical Services

## Slide 12: Integration Planning
Asked to look at common functions and services in the two library systems and identify possible efficiencies; and also identify policies to be harmonized or new procedures that will need to be developed.
The recommendations of the Work Groups were to be used by the Dean and Director for the consolidated integration plan as a basis for implementation of the integration.

## Slide 13: Integration Planning
Conceptually:
The overriding goal of the HSCL – Smathers integration was to ensure that services to our users were not compromised and it was hoped that work efficiencies and service quality would improve.
A report from each work group was submitted by February 25th.

## Slide 14: Integration Planning
Working Group recommendations fell into 4 general categories:
  Fully Integrate
  New support for HSCL
  More integrated decision making and communications
  No Integration

## Slide 15: Integration Planning
Fully Integrate:
Administrative Services (Human Resources and Financial Services)

## Slide 16: Integration Planning
New support for HSCL:
Development (Grants, PR)
Digital Services/Institutional Repositories
Facilities

## Slide 17: Integration Planning
More integrated decision making and communications:
Access Support (ILL, Circulation, Library-Wide Policies)
Public Services/Collections Management
Technical Services

## Slide 18: Integration Planning
No Integration:
Systems (IT)

## Slide 19: Integration Planning
In March 2009, Dean and Director, with input from other library staff, drafted the integration proposal to present to the Provost. The report covered:
• Integration
• Appropriate Funding for HSCL
• HSCL Renovation

## Slide 20: Integration Planning
As part of the Budget Preparation group, the Dean and Director had worked on the identification of critical funding needs at the HSCL and proposals for how to address these in order to improve services to HSCL patrons.

## Slide 21: Integration Planning
The report was posted on the internet and blog established for feedback from library employees and others on campus.
The plan was approved by the Provost, with an effective integration date of July 1, 2009.

## Slide 22: Other Considerations
In February, 2009, current and possible HSCL representation on relevant governance, management, technical and advisory committees of the Smathers Libraries was reviewed by Dean and Director.

## Slide 23: Other Considerations
In the spring of 2009, UF experienced critical state budget cuts.
The two systems engaged in a prolonged and detailed planning process in which prioritized areas, functions resources and positions for possible cuts were identified.
As a deliberate result of these priorities established by Dean and Director, the Smathers Libraries absorbed these FY 09-10 cuts entirely, sparing the budget of the HSCL.

## Slide 24: Implementation
On July 1, the HSCL Director became Associate Dean and Director of the HSCL, reporting directly to the Dean of University Libraries who in turn reports to the Provost
Director retained an non-reporting relationship with the VPHA

## Slide 25: Implementation
Centralized Fiscal Services and Human Resources offices of the Smathers Libraries were established.
2 fiscal positions were transferred from HSCL.
FY 08-09 year end reports for the HSCL were generated and publicly posted and the FY 09-10 budget for the HSCL was established and allocated based upon directives of the HSCL Director.

## Slide 26: Implementation
Beginning July 1, 2009, the Smathers Fiscal Services office produced, per HSCL specifications, and publicly posted monthly budget reports for the HSCL and maintained segregated fiscal accounts for the HSCL to ensure funds were not comingled between the HSCL and the rest of the integrated libraries.*
Director retained authority over funds of the HSCL.*
*Communicating a sense of ownership to the HSC colleges.

## Slide 27: Outcomes
No layoffs
Minimal reassignments
No reallocations of recurring funds

## Slide 28: Outcomes
Integration allowed us to pool resources in those areas that we serve in common, which allowed the integrated library system to devote more time and resources to the areas that we each uniquely serve.

## Slide 29: Successes @ UF
The centralization of the fiscal & human resources management functions provided a net savings of 1 HSCL FTE that was then repurposed to serve in a Access Services position, which in return, freed 1 full time librarian to serve the area of consumer health and community outreach.

## Slide 30: Successes @ UF
Further, at the Borland Library, a Senior Fiscal Assistant position was reclassified to a Library Assistant II when the job responsibilities were changed from strictly fiscal processes to include more time spent on the reference desk.

## Slide 31: Successes @ UF
HSCL had never participated in the University’s dual career program, but as a part of the University Libraries, the HSCL was able to place a Basic Biomedical Sciences librarian.
The HSC Libraries received one of the Provost’s ‘jumpstart’ positions - a Clinical Research Librarian. This position is critically important for the HSC, and it seems much less likely to have been funded had not the HSCL’s request been part of the proposal submitted by the integrated library system.

## Slide 32: Successes @ UF
Integration allowed HSCL staff to participate for the first time in the Smathers’ MiniGrant Program – a competitive internal award program that supports projects benefiting patrons.
  The most recent HSCL award evaluated the use of tablets for point-of-care information services.

## Slide 33: Successes @ UF
The combined system realized a change to the campus DSR funding method that provides the Libraries with a percentage of campus IDC rather than a fixed dollar amount, thereby allowing for future growth in pace with University research growth.
  The increased funding was added to the base HSCL material budget.

## Slide 34: Successes @ UF
Smathers Libraries provides funds to the HSCL for a variety of purposes, including a contract with an architect to begin planning for a phased renovation project. At the same time, the Dean has tirelessly pursued renovation funds.

## Slide 35: Successes @ UF
Significant pay inequities existed for the HSCL employee salaries when compared to the Legal Information Center and the Smathers Libraries. This represented a major obstacle to a successful integration.
  Smathers’ HR successfully completed a review for faculty and staff, and implemented market equity plans (primarily, using HSCL funds).

## Slide 36: Successes @ UF
The HSCL gained advocacy from the library Development Office including a grants manager. The HSCL had no such resources prior to integration and effectively competed for donors versus HSC units.
  Recently, the HSCL Director position was endowed!

## Slide 37: Challenges @ UF
The need to include all library employees regardless of location when planning meetings, special events and other activities is a clear challenge.
While distance can be solved by using technologies such as teleconferencing, the time demands related to being part of a large integrated library system are consequential.

## Slide 38: Results
Success is possible with planning and communication.
Integration can address historic issues, inequities, and inefficiencies, and can allow leveraging of resources.

## Slide 39: Results
The head of the new system, as a Dean, is positioned to serve as champion for the health libraries and integration may actually improve the standing of the libraries in the health center.
The initial focus is on just achieving a functional integration, but true cooperation and opportunities may take time.

## Slide 40: Pearls of Wisdom
Get on with it and implement to the best advantage of the libraries: patrons and staff are what matters and will suffer if leaders are not devoted.
Trust must be developed through tact, honesty and effectiveness.

## Slide 41: Pearls of Wisdom
Be candid about disadvantages to both units and mitigate these as best as possible.
Be candid about advantages to both units and celebrate progress towards these.

## Slide 42: Pearls of Wisdom
Clarify the scope of authority.
Consider maintaining distinguishable resources.
Collaborate on important decisions.

## Slide 43: Pearls of Wisdom
Communicate the health library
still belongs to those colleges.

## Slide 44: Pearls of Wisdom
Learning and improvements will flow and harmonize both ways between the integrated systems.

## Slide 45: Pearls of Wisdom
Periodically assess the integration and results.

## Slide 46
Around the Horn:
How the UF Successfully
Fielded a Team
that Integrates
Health Science and University Libraries
ufdc.ufl.edu/AA00011332
Thank you!