## Slide 1: Planning and Managing Digital Projects
John Nemmers and Mark Sullivan
University of Florida Smathers Libraries

## Slide 2: Section 1: Overview & Project Planning

## Slide 3: A Digital Project…
Has a time frame (start/end dates)
Has a scope/purpose
Has a project manager
Requires resources/inputs
Has a work plan
Produces digital outputs
Notes: The project is temporary but may lead to ongoing activities. A project has a definite beginning and an ending date. It is temporary; the project ends once the objectives have been met and the product or service exists.
Scope/purpose: Why is the project necessary? Projects are designed to solve a particular problem (create a unique product/service)
Project manager determines whether you have the skills, knowledge, and resources needed to accomplish the project’s goals. If you don’t, then you will have to find those resources, knowledge, and skills or the project may fail.

## Slide 4: Digital Project Breakdown
1/3 effort = project planning, pre-imaging preparation, preservation, oversight, evaluation
1/3 effort = description, metadata creation, database creation/maintenance
1/3 effort = digitization

## Slide 5: Questions to Answer:
Who will be served by project?
Have we identified the Primary/Secondary/Other audiences?
What will be digitized?
What are our priorities?
What will be the impact on the institution?
How much should we digitize?
What is our timeline? Start/end dates?
Notes:     Scholars, educators, college students, K-12, genealogists, general public
  Priorities: what is cool, what is in high demand, what is underused and should b made known/available
  Who decides priorities? Can be admin, external, funding agencies
  How much: everything in all the collections, representative samples

## Slide 6: Questions to Answer:
What resources do we need to support project?
What are funding sources?
Will project activities be undertaken in-house or outsourced?
What standards and best practices will be adopt?
What technologies will we use to create/maintain/deliver/preserve digital objects?
What is our sustainability plan beyond the project end?
Notes:   Resources: Space? Staff? Equipment? Total?
  Funding: internal, donor, grant
  Outsourcing - Issues with the security, safety, transportation of fragile material
  In-house: costs of labor/benefits, equipment, software
    In-house: Extant/newly developed software tools or buy vendor product or use partner technology (e.g, DLoC)
    In-house: Training and staff time (hire new staff, who does the work of permanent staff while working on project)
Sustainability: long term maintenance of the digital collection

## Slide 7: Initial Steps in the Process
Identify holdings to be digitized
Identify stakeholders and participants (internal/external)
Create a planning team
Determine project goals/objectives
Environmental scan of other projects
Identify needed resources
Develop work plan with timeline of activities
Notes:   The work plan is the road map that guides how resources are put into use over a specific period of time to produce products/services

## Slide 8: Identify Holdings for Digital Projects
Archival collections (papers, photos, AV, etc.)
Special collections
Reformatting microfilmed holdings
Born digital holdings
Digitization projects with partner holdings
Notes: Logical to focus on unique or rare objects (no need to duplicate effort)
Reformatting non-print resources: AV, microfilm, photos
Digitization for commercial purposes
  Born digital ex: IR
  External partners may have complementary resources

## Slide 9: Selective Digitization
Focus on holdings with high research/educational /commercial value
Often not feasible to digitize everything -> representative sample
Not everything merits digitization
Are the originals fragile/in jeopardy?
Rights? No known copyright holder -> Take down notices are option.
Permissions? Deed of gift?

## Slide 10: What are Priorities
Researcher demand?
Preservation?
Administrative mandate?
Donor driven?
Matching priorities of funding agency/partners?
Exposing hidden collections to increase use?

## Slide 11: Prioritizing Example: Everglades Collections at UF
Collections in demand
Hot subject area
Preservation issues
Easy formats
Viable funding source
Notes: May Mann Jennings, Gov Broward, Gov Jennings, Thomas Will, etc.
Environmental history: Everglades, drainage, flood control, development, conservation
high use of fragile materials almost 100 years old
Papers and Photos
NHPRC cost-effective digitization grants

## Slide 12: Potential Stakeholders/Participants
Archivists/Curators
Imaging personnel
Metadata personnel
Cataloging personnel
IT/Web personnel
Preservation or Conservation personnel
Advisors (e.g. panel of subject specialists)
Development/Fundraising personnel
Grant writer/manager
Administration
Donors
PR/Marketing personnel
External partners
Vendors
Notes: Successful projects have a core team of committed stakeholders
Stakeholders are any folks who can influence/contribute/make use of the project outcomes

## Slide 13: Creating a Team
Need for clear leadership (project manager or co-managers)
Consensus-building
Group decision-making
Expect resistance (both justified and not)
Admin support usually = successful elimination of resistance
Notes: Project manager may be any of the stakeholders but often is the collection manager/subject specialist
Project manager is responsible for leading communication, forming team, developing work plan, overseeing implementation, and evaluating outcomes

## Slide 14: Collaboration & Partnerships
Gain holdings/knowledge/support/IT from partners
Shared knowledge/experiences can lead to better workflow/products
Some granting agencies favor collaborative digital projects
Requires better communication/negotiation of expectations/activities/outcomes

## Slide 15: In-House vs. Outsourcing (or Hybrid)
Outsourcing costs can be lower if infrastructure/expertise not already in-house
Vendors set up to handle high volume; have equipment, training, software
Vendors often offer multiple services in addition to imaging
Vendor security risks – materials going off site/out of country (loss of control)
Have to evaluate, select, contract and communicate with vendors
Notes: Communication with vendors is a big deal. They may not understand archival importance. Your project may be small fries to them.

## Slide 16: In-House vs. Outsourcing (or Hybrid)
In-house projects lead to in-house expertise/infrastructure, but can require significant start-up costs
Complete control over in-house projects (fewer security risks)
Other pros/cons?
Hybrid approach: use vendors to handle one portion of project (e.g., only imaging)

## Slide 17: Common Outsourced Activities
Scanning
Transcription (e.g., oral histories)
Translation
Metadata creation
OCR
Database management
Online hosting
Preservation

## Slide 18: Planning Discussions
Brainstorming!
Consider all ideas/options
Identify impacts
  Staffing (extant or hire new or outsource)
  Space, equipment, software
  Impact on regular workflow
  Holdings (e.g., preservation/access issues)
Evaluate all info and make decisions

## Slide 19: Base Decisions on Data
Review/gather statistics
  Extent (e.g., # of page images)
  Reference/Usage statistics
  Scholarship produced based on holdings
Can create surveys/suggestion forms
Focus/advisory groups
Notes: Explain how we averaged Swamp folders to estimate extent

## Slide 20: Work Plan Development
Work plan focuses on quantifiable goals (e.g., producing a certain # of images)
What steps/activities will you implement to achieve goals?
Shows how inputs/resources are used to produce outcomes/products
Detailed budget (calculate all costs)
Notes: Need a clear idea of what you want to accomplish. What will the project solve? It will be difficult to evaluate success/failure without clear focus.
Can’t talk about the work plan without also talking about the budget

## Slide 21: TIP! Review grant guidelines, which usually call for:
Specific goals and objectives
Scope of project
Description of the materials and their importance/significance
Budget templates
Scanning/Metadata standards
Specific work plan
Evaluation criteria
Notes: NEH/NHPRC/IMLS/LSTA/etc.

## Slide 22: Work Plan
Projects usually have phases and benchmarks as part of a project timeline
Project activities are tied to project goals
Activities also tied to project resources
Identify staff – who (extant or new), how much time needed, etc.
Identify space, equipment, supplies needed (extant or new)
Notes: New digital initiatives usually have high start up costs. Hardware may include computers or server space.
Labor usually is the largest percentage of costs in a digital project
Staff: what % of an employee’s time will be committed to project (in grants, the salary & benefits are “In-Kind” costs shared by the institution towards the total project cost)

## Slide 23: Work Plan
Identify other costs (e.g., consultants, vendors, training, travel, shipping)
Hidden costs (administrative, PR) – can be cost share in grants
Technology issues: software/hardware/metadata/standards

## Slide 24: Work Plan
Work plan provides details about workflow / methodology
Simple workflow:

## Slide 25: Project Timeline Example
Months | Actions | Steps | Responsibility
1-3 | Hire/train staff; buy equipment/supplies | Interview candidates; training | Project manager, digital supervisor
3-12 | Scanning and Metadata creation | Scanning, QC, loading into system | Digital technicians; IT experts
13-16 | Evaluation, promotion | Focus groups, listserv emails, presentations, journal article | Project manager; publicity dept, project staff

## Slide 26: Gantt Charts
Source: http://en.wikipedia.org/wiki/File:GanttChartAnatomy.png

## Slide 27: Possible Project Budget Items
Salaries & Benefits
Hourly wages for temp staff
Vendors
Consultants
Equipment /supplies
Training/travel
Indirect Costs

## Slide 28: Hardware Options
Scanners (flatbed, ADF, slide, etc.)
Digital cameras
AV conversion
Servers (storage, delivery, etc.)
Notes: Remember costs of migration to new hardware in future

## Slide 29: Software Options
In-house development:
  Requires programmers/database admins/metadata specialists
  Requires constant maintenance/testing
Off-the-shelf software:
  E.g., Photoshop, DigiTool
  Requires knowledge/evaluation/comparison of vendors
  How will software be upgraded/maintained?

## Slide 30: Sustainability Considerations
Digital technology is constantly/rapidly changing
Upgrade/replacement of software/hardware
Migration of digital objects/metadata
Costs of long term digital preservation
Costs of staffing over time (managing content, hardware/software)

## Slide 31: Exercise 1: Entire Group
Handout includes a description of holdings to be digitized, target audience and other pertinent info
Create goals for project
List activities to achieve those goals

## Slide 32: Exercise 1: Goals & Activities
Goal 1:

## Slide 33: Section 2: Implementing Digital Projects

## Slide 34: Implementing Digital Projects
Imaging Theory & Best Practices
Digitization Equipment
Metadata for Digital Resources
Digital Asset Management Software
Archiving and Preserving Digital Projects

## Slide 35: Section 2.1: Imaging Theory & Best Practices

## Slide 36: Imaging Theory & Best Practices
Bit Depth & Color Space
Resolution
File Types
Image Compression
OCR
Questions

## Slide 37: Bit Depth & Color Space
Bi-tonal, “black and white”, 1 bit
Greyscales
  8-bit ( 256 shades of gray )
  16-bit (65536 shades of gray )
RGB ( usually 24-bit )
CMYK ( usually 32-bit )

## Slide 38: Bit Depth & Color Space
Image: © Nevit Dilmen found at Wikimedia commons
RGB “built” from 3 color channels

## Slide 39: Bit Depth & Color Space
Color Fidelity
“Full Informational Capture”
Meaningful color should be retained
Bi-tonal
8-bit Greyscale
24-bit Color
Notes: Readers of Latin religious texts, such as that seen above, will recognize the red text as instructions to the faithful, commentary on the spoken text of a religious service, or the narrative of the priest as opposed to that of the congregation’s response.

## Slide 40: Bit Depth… : Recommended
(Almost) never scan 1-bit
Completely grey items should (usually) be scanned 8-bit greyscale.
Items with meaningful color should be scanned 24-bit RGB
Trade-offs between quality and file size

## Slide 41: Bit Depth… : Rationale
Text – Optical Character Recognition

## Slide 42: Resolution
Resolution of an image expressed in pixels
PPI – pixels per inch
DPI – dots per inch

## Slide 43: Resolution : Recommended
Resolution | Use For
300 pixels per inch (ppi) | Printed text with normal sized fonts Oversized documents and maps Manuscripts with legible script
600 pixels per inch (ppi) | Photographs and select graphic arts Printed text with very small fonts Manuscripts with difficult scripts

## Slide 44: Resolution : Rationale 1
Newspaper graphics printed at 80 dpi
Magazine graphics printed at 120 dpi
High-end graphics printed at 300 dpi
Scanning at 300 dpi is sufficient

## Slide 45: Resolution : Rationale 2
Text – Optical Character Recognition

## Slide 46: Resolution : Rationale 3
Photographs
  Use 600 dpi
  Continuous-tone images
  Unexpected use – capture all details

## Slide 47: File Types
Save archival masters as TIFF
Internet delivery as JPEGs or JPEG2000s

## Slide 48: Image Compression
Save archival TIFFs as non-compressed
“Lossy” vs. Lossless compression

## Slide 49: OCR
Optical Character Recognition
Creation of plain text from an image file
Just as important is the positional information!
  Text highlighting
  Text analysis

## Slide 50: OCR : ALTO XML
LOC XML schema / standard
“Analyzed Layout and Text Object”
Contains position (and style) of each word, with possible variants
Can be embedded within a METS file
Used by NDNP

## Slide 51: OCR : ALTO XML

## Slide 52: Review of Topics
Bit Depth & Color Space
Resolution
File Types
Image Compression
OCR

## Slide 53: Questions? How about born digital?

## Slide 54: Section 2.2: Scanning Equipment

## Slide 55: Scanning Equipment
Flatbed scanners
Sheet-feed scanners
Book scanners
Map scanners
Microfilm

## Slide 56: Flatbed Scanners
Microtek ScanMaker 9800XL
Epson Expression 10000XL

## Slide 57: Sheet-feed Scanners
Panasonic KV-S2046C

## Slide 58: Book Scanners
i2S CopiBook ( 24-bit color )
Konica Minolta PS7000
with grayscale up-grade

## Slide 59: Oversized Document Scanners
Camera back, vacuum table, etc..
Betterlight Super 8K-HS

## Slide 60: Microfilm Scanners

## Slide 61: Section 2.3: Metadata for Digital Resources

## Slide 62: Metadata for Digital Resources
What is metadata?
What is your digital resource?
Standards
Standards Comparison
Tools
Questions

## Slide 63: What is metadata?

## Slide 64: What is metadata?

## Slide 65: What is metadata?

## Slide 66: Library and Museum Metadata

## Slide 67: Library and Museum Metadata
Greek Vase
470 –460 BC
35 centimeters
Odysseus and Eumaios the Swineherd
from Homer’s story of the Odyssey

## Slide 68: Library and Museum Metadata
Format: Greek Vase
Date: 470 –460 BC
Height: 35 centimeters
Title: [Greek Vase of Odysseus and Eumaiosthe Swineherd]
Notes: from Homer’s story of the Odyssey

## Slide 69: Library and Museum Metadata

## Slide 70: Library and Museum Metadata
Title: L' Isle St. Domingue
Alternate Title: Atlas portatif Universel..
Physical Desc: 1 Map. : col; 17 x 22 cm on sheet 23 x 32 cm.
Language: French
Creator: Robert de Vaugondy, Gilles , 1688-1766
Date: 1749
Place of Publ: Paris 1749
Subjects: Maps --Early works to 1800 --West Indies ( lcsh)
Maps --Early works to 1800 --Hispaniola ( lcsh)
Genre: single map( marcgt)
Maps ( lcsh)
Early works to 1800 ( lcsh)
Spatial Coverage: Haiti, Dominican Republic
Note: Outline color.

## Slide 71: Library and Museum Metadata

## Slide 72: Library and Museum Metadata
Title: Avanzamos o retrocedemos? : reflexiones sobre…
Physical Desc: 165 p.
Language: Spanish
Creator: Mejia, Radhames
Publisher: Santo Domingo : PUCMM/CIEDHUMANO
Date: 2010
Subject: Educacion-Republica Dominicana-Ensayos, conferencias
Abstract: Este libro recoge una serie de artaculos sobre temas educativos publicados en los aos 2006 y 2007 en el periodico El Caribe.
Identifier: RD 370.97293 M516a
isbn-9789945415339

## Slide 73: Library Metadata

## Slide 74: Library Metadata - MARC

## Slide 75: What is your digital resource?

## Slide 76: What is your digital resource?
Physical archival containers
  Archival box?
  Archival folder?
  Item-level?
Scrapbooks
  Pages
  Photographs
Newspapers
  Issues
  Article

## Slide 77: Metadata Standards

## Slide 78: Why metadata standards?

## Slide 79: Standards
“The nice thing about standards is there are so many to choose from.”
- Andrew Tannenbaum (1988 )

## Slide 80: Types of Metadata Standards
Bibliographic Description
Metadata “Wrappers” and Transport
Collection Descriptions
Other Standards
  Authority Standards
  Proprietary Standards
  etc…

## Slide 81: Types of Metadata Standards
Bibliographic Description
Metadata “Wrappers” and Transport
Collection Descriptions
Other Standards
  Authority Standards
  Proprietary Standards
  etc…

## Slide 82: Bibliographic Description Standards
MARC
Dublin Core
MODS
VRA Core

## Slide 83: Bibliographic Description : MARC
MARC
  Originally developed in 1960s by Library of Congress
  Most embraced metadata standard in libraries
MARC 21
  Combination of USMARC and CAN/MARC
  Metadata standard for 21st century
MarcXML
  Same MARC format, except encoded in XML

## Slide 84: Bibliographic Description : MARC
Positives:
  Can encode a very granular amount of data
  Very well adopted and works well with machine readers
Negatives
  Not very human-readable
  High learning curve
  Mixes data with display (as commonly implemented)

## Slide 85: Bibliographic Description : DC
Dublin Core
Originally developed between 1994 and 1995 in Dublin Ohio by OCLC
Used widely on web pages to assist search engines
Simplified Dublin Core
Title Creator Subject
Description Publisher Contributor
Date Type Format
Identifier Source Language
Relation Coverage Rights

## Slide 86: Bibliographic Description : DC
Qualified Dublin Core
  Added three elements ( Audience, Provenance, RightsHolder)
  More importantly, added some basic refinements
Positives
  Widely accepted and easy to read and encode
Negatives
  Even with qualified dublin core, difficult to encode complex data
  Lack of data refinement leads to loss of UI options

## Slide 87: Bibliographic Description : MODS
Metadata Object Description Scheme
Developed in 2002 by Library of Congress
Beginning to be the de facto standard for digital libraries (MODS/METS)
Positives
  Can handle a (large) subset of MARC tags
  Handles complex objects and can easily be extended
Negatives
  Hard to do round trip portability from MARC  MODS  MARC

## Slide 88: Bibliographic Description : VRA Core
Visual Resource Association
Developed in 1996 by Visual Resource Association
Used for describing visual/cultural materials
Includes all the standard tags
  Date, Title, Description, Rights, Subject, etc..
Also more unique tags
  Cultural Context
  Style
  Technique

## Slide 89: Bibliographic Description Standards
MARC
Dublin Core
MODS
VRA Core

## Slide 90: Types of Metadata Standards
Bibliographic Description
Metadata “Wrappers” and Transport
Collection Descriptions
Other Standards
  Authority Standards
  Proprietary Standards
  etc…

## Slide 91: Metadata “Wrappers” and Transport
Contents
  Files and Structural data
  Administrative data
Choices
  METS
  OAI-PMH
  No wrapper necessary

## Slide 92: Metadata “Wrappers” : METS
Metadata Encoding & Transmission Standard
Standard by Library of Congress (2001)
Contains
  Descriptions section(s)
  Administrative section(s)
  File section(s)
  Structure map(s)
Accepts any XML schema

## Slide 93: Metadata “Wrappers” : OAI-PMH
Open Archives Initiative -Protocol for Metadata Harvesting (2000-2001)
Defines a protocol (over HTTP)
Main Verbs
  Identify
  ListMetadataFormats – usually dublin core (99%)
  ListSets
  ListRecords

## Slide 94: Types of Metadata Standards
Bibliographic Description
Metadata “Wrappers” and Transport
Collection Descriptions
Other Standards
  Authority Standards
  Proprietary Standards
  etc…

## Slide 95: Collection Metadata Standards
(METS)
EAD
  Encoded Archival Description
  Electronic Finding Guide/Aid
  Main Sections
    Descriptions
    Container List –can link to digital objects

## Slide 96: Types of Metadata Standards
Bibliographic Description
Metadata “Wrappers” and Transport
Collection Descriptions
Other Standards
  Authority Standards
  Proprietary Standards
  etc…

## Slide 97: Still to come…
Authority Metadata Standards
  NACO
  MADS
  EAC
Other Standards
  KML
  DarwinCore
  Z39.50 / ZING
Standards are like weeds….

## Slide 98: Proprietary and Custom Formats
Proprietary File Formats
  Greenstone Document File (doc.xml)
  Fedora Object File (FOXml)
Custom Schemas
  SobekCM Schema ( UFDC and dLOC)

## Slide 99: Back to the beginning?
MODS?
KML?
MADS?
MARC?
To wrap?
Dublin Core?
VRA Core?
EAC?
EAD?
METS?

## Slide 100: Evidence-based
Universities within Florida ( 10 schools )
Digital Objects
  MARC ( linked to catalog )
  Dublin Core ( no wrapper, simple objects )
  METS wrapper ( for complex items )
  MODS
EAD for Finding Aids / Guides
OAI-PMH Harvesting

## Slide 101: “One standard to rule them all”

## Slide 102: “One standard to rule them all”
METS Wrapper

## Slide 103: “One standard to rule them all”
METS Wrapper
DC  MODS
Additional custom metadata

## Slide 104: “One standard to rule them all”
METS Wrapper
Dublin Core
Additional custom metadata

## Slide 105: “One standard to rule them all”
METS Wrapper
MODS
Additional custom metadata

## Slide 106: “One standard to rule them all”
METS Wrapper
MODS
Additional custom metadata
VRA Core
Darwin Core

## Slide 107: “One standard to rule them all”
METS
MODS
SobekCM
Archival
Service
Greenstone

## Slide 108: “One standard to rule them all”
METS
MODS
SobekCM
Archival
Service
Fedora,
ContentDM, etc…

## Slide 109: Standards Comparison
Link to external comparison
http://digital.uflib.ufl.edu/development/standards_comparison.pdf

## Slide 110: Lessons / Standards Conclusions
Try not to tie your metadata to your system
  Archival vs. Service
Don’t be afraid of extending for your own needs, but continue to follow the standards
Don’t cripple your metadata / Prepare for the most information you would want
  METS / MODS v. simple Dublin Core

## Slide 111: Tools

## Slide 112: Metadata Tools
Library of Congress site of METS utilities
  http://www.loc.gov/standards/mets/mets-tools.html
SobekCM METS Editor (UF)
  http://ufdc.ufl.edu/metseditor
MarcEdit Tool
  http://people.oregonstate.edu/~reeset/marcedit/html/index.php

## Slide 113: Review of Topics
What is metadata?
What is your digital resource?
Standards
Standards Comparison
Tools

## Slide 114: Questions?

## Slide 115: Exercise 2: Individual
Handout includes descriptive info for an object that will be digitized
Map from non-standard source metadata to Dublin Core
Notes: Show importance of standards, interoperability, etc.
Use this: This is a fairly typical mapping requirement. In order to create a union catalog of disparate resources, or share metadata from various different sources and systems, we need a common metadata format to map into. Simple DC is often selected for such purposes. Simple DC is also the minimum metadata format for metadata harvesting via the Open Archives Initiative Protocol for Metadata Harvesting (OAI-PMH). In other words, if you wish to allow information about the content of your collections to be harvested via OAI, you must at least provide a simple DC record for every resource (you can provide richer metadata).

## Slide 116: Section 2.4: Digital Asset Management System

## Slide 117: DAMS
ContentDM
DigiTool
Omeka
Greenstone
Fedora
Dspace
Custom ( SobekCM )
Notes: Show importance of standards, interoperability, etc.
Use this: This is a fairly typical mapping requirement. In order to create a union catalog of disparate resources, or share metadata from various different sources and systems, we need a common metadata format to map into. Simple DC is often selected for such purposes. Simple DC is also the minimum metadata format for metadata harvesting via the Open Archives Initiative Protocol for Metadata Harvesting (OAI-PMH). In other words, if you wish to allow information about the content of your collections to be harvested via OAI, you must at least provide a simple DC record for every resource (you can provide richer metadata).

## Slide 118: Archival Information System
Archon
Archivist Toolkit
ArchiveSpace
Notes: Show importance of standards, interoperability, etc.
Use this: This is a fairly typical mapping requirement. In order to create a union catalog of disparate resources, or share metadata from various different sources and systems, we need a common metadata format to map into. Simple DC is often selected for such purposes. Simple DC is also the minimum metadata format for metadata harvesting via the Open Archives Initiative Protocol for Metadata Harvesting (OAI-PMH). In other words, if you wish to allow information about the content of your collections to be harvested via OAI, you must at least provide a simple DC record for every resource (you can provide richer metadata).

## Slide 119: Section 2.5: Archiving and Preservation of Digital Projects

## Slide 120: Digitization: One Puzzle Piece
Digitization is one piece of a digital preservation plan, but only one piece
Without the rest of the puzzle, digitization is ultimately useless for preserving and archiving our historical and cultural resources
Include Digital Preservation and full lifecycle of the image and data in all digitization plans.

## Slide 121: Preservation and Long-Term Access Through Networked Services Project Survey
Surveyed over 200 organizations, mostly European archives and libraries
  Digital content volume to increase 25-fold over next decade
  70% of respondents expect to hold over 100TB of content
  Only 47% of organizations had an allocated budget for digital preservation
  (http://www.planets-project.eu/publications)
Large-Scale Digitization

## Slide 122: Digital Preservation Is…
Digital preservation is:
  Active
  Constant process
  Exponentially multi-tiered
  About ensuring continuing accessibility
  Relatively new and somewhat in its infancy

## Slide 123: Digital Preservation is NOT…
Compact Disks
  2002 – 6,000 CD’s ( 2.6 TB )
  2008 – 23,000 CD/DVD ( 48 TB )
  Unmanageable
  Slowly deteriorating
Two (or 3 or 4) copies

## Slide 124: Table of Contents
What to preserve? How do I know it is preserved?
Object-level Preservation
File-level Preservation
Organizational: Trustworthy Digital Repositories
Recommendations
Questions

## Slide 125: What to Preserve?
How do I know it is preserved?

## Slide 126: What to preserve? How do I know it is preserved?
Text-level preservation?
Aujourd'hui premier janvier dix huit cent quatre, le Général en chef de l'Armée indigène, accompagné des généraux, chefs de l'armée, convoqués à l'effet de prendre les mesures qui doivent tendre au bonheur du pays:
Après avoir fait connaître aux généraux assemblés ses véritables intentions d'assurer à jamais aux indigènes d'Haïti un gouvernement stable, objet de sa plus vive sollicitude : ce qu'il a fait à un discours qui tend à faire connaître aux puissances étrangères la résolution de rendre le pays indépendant, et de jouir d'une liberté consacrée par le sang du peuple de cette île ; et, après avoir recueilli les avis, a demandé que chacun des généraux assemblés prononçât le serment de renoncer à jamais à la France, de mourir plutôt que de vivre sous sa domination, et de combattre jusqu'au dernier soupir pour l'indépendance.
Notes: Encoding concerns remain

## Slide 127: What to preserve? How do I know it is preserved?
Text-level preservation?
Today, January 1, 1804, the General in Chief of the Indigenous Army, accompanied by generals and army chiefs convoked in order to take measures tending to the happiness of the country:
After having made known to the assembled generals his true intention of forever ensuring to the natives of Haiti a stable government — the object of his greatest solicitude, which he did in a speech that made known to foreign powers the resolution to render the country independent, and to enjoy the liberty consecrated by the blood of the people of this island; and, after having gathered their opinions, asked each of the assembled generals to pronounce a vow to forever renounce France; to die rather than to live under its domination; and to fight for independence with their last breath.

## Slide 128: What to preserve? How do I know it is preserved?

## Slide 129: What to preserve? How do I know it is preserved?
“It is the actual information content of a document, data-set, or sound or video recording that should be preserved, not the Microsoft Word file, or the Excel spreadsheet, or the QuickTime movie.”
    - Angela Dappert and Markus Enders (British Library) “Digital Preservation Metadata Standards.” Information Standards Quarterly. Spring 2010.
Also the context and layout though.

## Slide 130: Object-Level Preservation

## Slide 131: Object-Level Preservation
More than just the images and text (but also!)
Descriptive Information
  Describes the intellectual entity ( title, author )
  Same information used for discovery and display of object
Structural Information
  Table of contents, page order
File Information
  File size
  Checksums and digital signatures for fixity and authenticity checks
Administrative Information
  Provenance and access conditions for the object

## Slide 132: Object-Level Metadata
METS
  Metadata Encoding and Transmission Standard
  Descriptive Metadata Container
    MODS ( Metadata Object Description Standard )
    Dublin Core
    VRACore ( Visual Resource Association )
    MarcXML
  Structural Metadata
  Technical File Metadata
  Administrative Metadata

## Slide 133: PREMIS
PREservation Metadata : Implementation Strategies
Metadata needed to support preservation
Contains what “most working repositories are likely to need to know” ( Dappert and Enders )
HUGE data dictionary – must pick and choose
Describes historical preservation actions/agents
Provides information needed for any future preservation actions
Can be encoded in METS file

## Slide 134: PREMIS

## Slide 135: PREMIS

## Slide 136: File-Level Preservation

## Slide 137: Necessary Preservation File Information
Example PREMIS Image Record
  Checksums and Size
  Preservation Level ( full, bitwise, etc.. )
  Behaviors
  Format ( MIME, Format Registry, Validation Info )
  Creating Applications
  Capture Information (MIX)
  Environments ( software, operating system, processor, hardware )
  All migrations events

## Slide 138: File Format Migration / Emulation
Any sound preservation strategy must deal with the ephemeral nature of file formats
Migration v. Emulation
Must either constantly migrate forward or at least have a migration strategy
Migration strategy is also ephemeral and represents best current options

## Slide 139: Recommended File Formats
Four basic criteria
  Specification must be freely available
  Must be no patents or licenses on the format
  Other digital repositories using or endorsed format
  Variety of tools for writing and rendering format

## Slide 140: Recommended File Formats
Migration strategy is also ephemeral and represents best current options
Archivematica ( UNESCO preservation system )
  Presented with a .WMV ( Windows Media Video ) proprietary file
  Current strategy: Convert to MPEG-2
  Future strategy: Convert to Motion JPEG2000

## Slide 141: Organizational: Trustworthy Digital Repositories

## Slide 142: Alexandria Library

## Slide 143: Alexandria Library

## Slide 144: Digital Preservation Community Process Models
Open Archival Information System (OAIS)
  Preserving Digital Information published by Task Force on Archiving Digital Information in 1996.
  Draft OAIS reference model published in 1999
  Primary benchmark and chief process model for the preservation of digital assets
InterPARES
  International Researchon Permanent Authentic Records in Electronic Systems.
  Focuses on records maintenance
Digital Curation Centre: Curation Lifecycle Model
  Defines three levels of preservation and best practices for each

## Slide 145: OAIS Reference Model
Provides framework for understanding of archival concepts needed for long term digital information preservation and access
Provides concepts needed by non-archival organizations to be effective participants in the preservation process
Provides framework for describing and comparing different strategies and techniques
Provides basis for comparing data models of digital information preserved and how they change over time
Guides the identification and production of OAIS-related standards

## Slide 146: An OAIS must:
Negotiate for and accept appropriate information from producers
Obtain enough rights to ensure long term preservation
Determine the designated community
Ensure preserved objects are independently understandable to designated community
Follow documented policies and procedures which ensure the information is preserved against all reasonable contingencies
Ensure object can be disseminated as authenticated copies of the original or the original
Make preservation information available to designated community

## Slide 147: Toward Certified Digital Repositories
Where are we?
  Granular standards (PREMIS)
  Process Models (OAIS, InterPARES)
In 2000, RLG and OCLC published Trusted Digital Repositories: Attributes and Responsibilities
This inches us closer, by defining a Trusted Digital Repository and expands the discussion to include the policies, standards, as well as technology infrastructure as a trusted system.

## Slide 148: Developing Metrics for Certification
Nestor Catalogue of Criteria for Trusted Digital Repositories
  Network of Expertise in Long-term Storage of Digital Resources
  Provides:
    Information and criteria for self-assessment for digital repositories
    Training Tools
    Iterative process – Documentation, Transparency, Adequacy, and Measurability

## Slide 149: Developing Metrics for Certification
DRAMBORA
  Digital Repository Audit Model Based on Risk Assessment
  Digital Curation Center (DCC) and Digital Preservation Europe (DPE)
  Focuses on risk identification, risk prioritization, and risk mitigation of risks through six step process of self-assessment.
  Developed from a TRAC-based self-assessment originally

## Slide 150: Developing Metrics for Certification
TRAC
  Trusted Repositories Audit & Certification Criteria & Checklist
    Research Libraries Group (RLG) and U.S. National Archives and Record Administration (NARA)
    2005 - Grant from Andrew W. Mellon Foundation to develop procedures and activities to audit and certify digital archives.
    2007 - Final publication includes 84 criteria
      Organizational infrastructure
      Digital object management
      Technologies (IT and security)
    Two repositories ( Portico and HathiTrust ) initially audited
    Portico certified as a trustworthy digital repository for CRL community

## Slide 151: Toward Standards
Conformity Assessment Requirements for Bodies Providing Audi and Certification of Management Systems ( ISO/IEC 17021 ) is current international standard applied
Audit and Certification of Trustworthy Digital Respositories ( CCSDS 652.0-R1, ISO/DIS 16363 ) still under development as an ISO standard
Requirements for Bodies Providing Audit and Certification of Candidate Trustworthy Digital Respositories also under development as an ISO standard

## Slide 152: Archiving Recommendation

## Slide 153: Recommendations
Be aware of the ongoing cost of preservation and plan according
Be a part of something larger
  Subject-based trusted repositories
    LLMC ( Law Library Microform Consortium )
  Regional and International trusted repositories
    HathiTrust
    Florida Dark Archive / State Universities

## Slide 154: Review of Topics
What to preserve? How do I know it is preserved?
Object-level Preservation
File-level Preservation
Organizational: Trustworthy Digital Repositories
Recommendations

## Slide 155: Questions?

## Slide 156: Section 3: Evaluation & Project Wrap-up

## Slide 157: Project Wrap-Up
Evaluation of success/failure
Promoting both products and the project itself
Final report for funding agencies
Future testing to improve products/services (e.g., usability, focus groups, surveys)

## Slide 158: Project Wrap-Up: Questions
What was final per-item cost?
What would you change if you had it do over again?
Were the products worth the expense/effort?
What did we learn from failures/mistakes?

## Slide 159: Assessing/Measuring Success
Determine criteria for measuring success at start of project
Choose method most appropriate for project (or required by funding agency):
  Summative Evaluation
  Outcomes-Based Evaluation
Best evaluation is both during and after
Difficult to assess if user needs met

## Slide 160: Summative Evaluation
Did we meet/not meet goals of the digital project?
Did we meet goals on time?
Were resources (staffing, budget) enough to get job done?
Includes evaluation of workflow and activities
Usually includes both quantitative and qualitative measures
Notes: Quantitative measures: size of digital collection, number of metadata records, number of page views, number of visits
Qualitative measures: usability, functionality, user satisfaction and needs met (info collected from focus groups, online surveys, interviews, etc.)

## Slide 161: Outcomes Based Evaluation
Shows if goals of the digital project were met/not met
User-centric (how have patrons benefitted)
Focus is on impacts/benefits of project rather than on activities
Includes evaluation of staffing, workflow, budget (were they enough to get job done)
Includes quantitative and qualitative measures
Encouraged by many grants
Notes: How has the project made a difference/impacted users?

## Slide 162: Components of Outcomes-Based Evaluation
Inputs/Resources
Activities
Outputs/Products
Quantifiable outcomes (e.g., # of users able to access holdings will increase)
Evaluation indicators
Methods/Sources for Evaluation
Notes: Outputs: # of images scanned, # of metadata records, online pages, project documentation, lesson plans, etc.
Outcome: Public (scholars, students, general) uses technology to access primary sources pertaining to Florida history
Indicator: # of views of digital objects online
Measure: Usage statistics from server logs

## Slide 163: Promotion/Publicity
Fairly standard for most projects
Traditional methods: newsletters, releases, listservs, presentations, journal articles, etc.
Newer methods: facebook, blogs, youtube, flickr, other social networking

## Slide 164: Questions?

## Slide 165: Exercise 3: Entire Group
Use list of project goals/activities created in Exercise 1
Create evaluation plan (summative or outcome-based)