LIBRARY SERVICES & TECHNOLOGY ACT GRANTS

MID-YEAR REPORT

For Federal Fiscal Year 2005 Projects

Due:  April 1, 2006

Library/Organization  University of Florida Libraries

Address P.O. Box 117007 City Gainesville Zip 32611

Phone (352) 846-0129  SUNCOM ________________________________

Project Name Rewiring Florida’s News

Project Number 05-LSTA-F-13 Grant  Award  $95,000

I.  EXPENDITURES

Use the attached Expenditures page to provide a status report of project expenditures to date detailed by category and source of funds.

Grant Funds

- Resulting from a mis-communication between UF Division of Sponsored Research (DSR) and the awarded Department, Digital Library Center, funds were delayed in coming to the Center – arriving in the second quarter of the grant.  DSR failed to pass along request for budget revision.

- Resulting from an additional mis-communication, this time from the Libraries Grants Office to DSR, funds received were not released for expenditure until early February 2006.

- Equipment bids per UF regulation are now out to vendors (more below).

Institutional Contribution

- Center staff (student assistants) have been contributing time for the collation and preparation of newspapers for imaging pending equipment availability.

- Center staff (permanent staff not listed as cost share & not included on Expenditures report) concluded copyright (i.e., Internet Distribution Rights) with newspaper publishers, procuring rights to all but one of the titles originally listed as potentially available for digitization.

- Center staff (permanent staff not listed as cost share & not included on Expenditures report), using other imaging equipment already in-house have imaged newspapers from the historic queue described by the grant (more below).

II.  OUTCOMES PLAN

Attach the current outcomes plan for the project.  If there are any changes in the project activities, outcomes or evaluation, they should be identified in this plan.

- Funding availability delays have pushed schedules back.  We are in the process of acquiring new-to-market faster technologies and more scanner units to push production toward completion target dates.

- We will phase project deliverables: page images in chronological hierarchy in a first phase and text search in a second phase as we implement and test newly designed software.

III.  STATUS REPORT

Describe the extent to which the project is meeting its outcomes.  Discuss project activities and how the library is using data collected to improve the project.

- Funding availability delays have made it difficult to meet the outcome targets we had hoped to meet by this date.  Again more and faster technologies have been identified and are starting to be deployed to speed us toward targets.

- Delays and the natural inclination to find better technologies have also led us to develop a relationship with a technology vendor’s design team.  To the extent that they plan to share our story, nationally and internationally, Florida (the State and University) will be seen as a model.

- Florida (this project specifically) is the only state project to attempt, on the scale of more than a handful of newspapers, to seek permissions from publishers.  
Our counterparts in Georgia and Kentucky, for example, have reported that they avoided similar projects fearing copyright complications.  Georgia has continued microfilming under increasing pressure from aging equipment, limited supplies, and distribution systems.  Kentucky has placed its filming program on hiatus as it considers its options.  Similar reports are coming from NDNP project institutions, fearing that newspaper publishers will demand continuing fiscal compensation for continued public access to their states’ newspapers.
Florida small and medium sized independent newspaper publishers have allowed us Internet Distribution Rights freely, with only one exception.  Most see distribution rights as a trade: distribution in exchange for free archiving.  Some see the long term availability of their newspapers with the hope that long term use may support increase advertising revenue generation.  Most, however, when they have said something, have indicated that they are acting in the community interest.  
Some of our newspaper publisher contacts have taken this concept further.  And, again, here too, Florida is a.  With electronic markup, they’ve suggested that they may give us the electronic files obviating digitization entirely, together with start-up funding.  (Unfortunately, consideration of this project extension must wait until we’ve launched this LSTA project’s more rudimentary routines for the much larger number of newspapers that do not yet compose electronically.)

- The success of this project very much depends upon our ability to bring additional resources to the table.  UF, as committed, will bring Student Assistant cost share to the table; but it is also bringing additional resources:

  - More than $70,000 in library and endowment budget for additional equipment

  - More than $9,000 in endowment budget for additional server storage space.

  - Development, through other granting, of additional text conversion systems priced at more than $18,000.

  - More than $11,000 in endowment budget for JPEG 2000 image compression software without which the very large (25 MB to 75 MB) digital files being created by the project could not be displayed to users in any reasonable time.  (N.B. the new JPEG 2000 server was recent brought on-line; and, we prepare to mount images for test delivery.)

  - More than $35,000 in programming staff time for the development of a user-friendly search and display interface over the top of Greenstone “freeware”.

I certify that all of the information contained herein is correct to the best of my knowledge.

____________________________________________________	2006 May 3

Signature of Project Principle Investigator	Date

_Erich J. Kesse  _____________________________________

Typed Name of Library Director

____________________________________________________	2006 May 3

Signature of Library Director	Date

_Dale B. Canelas_____________________________________

Typed Name of Library Director

LSTA Mid-Year Report

Library/Organization  University of Florida Libraries

Project I.D. Number  05-LSTA-F-13

Grant Award	 $ 95,000

I.  EXPENDITURES		LSTA	LOCAL/STATE

LSTA	FUNDS	MATCH

A. SALARIES & BENEFITS  (All salaries paid	EXPENDED	UNEXPENDED	EXPENDED

from both federal and local sources)

POSITION TITLE                              F.T.E.

Student Assistants________________   ________	$	_____________0			_____________0	$	14,475.50____

TOTAL SALARIES		$	_____________0		$	_____________0	$	14,475.50____

B. CONTRACTUAL SERVICES  (List each vendor)

Not required by grant		$	_____________0			0_____________	$	_____________0

TOTAL CONTRACTUAL SERVICES		$	_____________0		$	0_____________	$	____________0

C. LIBRARY MATERIALS		$	_____________0		$	0_____________	$	____________0

D. SUPPLIES		$	_____________0		$	0_____________	$	____________0

E. TRAVEL		$	_____________0		$	0_____________	$	____________0

F. EQUIPMENT  (Specify)

CopiBook Scanners (4)		$	_____________0		$	95,000________		____________0

TOTAL EQUIPMENT		$	_____________0		$	0_____________	$	____________0

G. OTHER  (Specify)

N/A____________________________________	$	_____________0		$	0_____________	$	____________0

TOTAL OTHER		$	_____________0		$	0_____________	$	____________0

H. TOTAL A-G		$	______________0		$	95,000_  ______	$	14,475.50____

Library/Organization  University of Florida Libraries

Project Name Rewiring Florida’s News

Project Number 05-LSTA-F-13 Grant  Award  $95,000

LSTA OUTCOMES PLAN

Activities:

- Hire, train, and supervise project staff
Existing staff employed, working toward project goals preparing newspapers for digitization.

- Purchase equipment
Purchase delayed resulting from internal mis-communications.  Bid now on the street – to close later this month.
Pending purchase, we are using pre-existing albeit slower equipment to advance items in the historical queue.  
1990 issues representing 103 titles have been digitized.
Additionally, pending project equipment, the Center has begun to use a scanner purchased (for $38,000 not listed on Expenditure  sheet, not needed for cost-share) with its Endowment funds.  We have been able to quickly digitize annual run of the Bradford County Telegraph.  We’ll continue to use this equipment as to recover lost time.
Incidentally, this new camera was not on the market when we drew up project bid specs.  UF Libraries has now committed funds for the purchase of an additional unit (at a lowered cost of $34,450 also not listed on Expenditure sheet, not needed for cost-share), which is slated for an early June arrival.
The new scanner performs with 4 times the speed of the originally specified equipment.  Grant bid is being redirected to this new unit, and additional scanners will be purchased.  The full compliment of scanners will give us the desired parity with microfilm cameras and allow us to take the full queue digital.

- Digitize, markup and serve all issues of designated newspapers between January 1, 2006 and June 30, 2006
See above.

- Create a newspaper digitization manual (from historic newspaper film sources)
In draft, pending reviewers comments and revision.
Final version will be compliant with U.S. National Digital Newspaper Program specifications.
Procedures are currently being pre-tested by U. Central Florida in its IMLS funded grant (n.b., funding for this pretest is not being accounted against UF’s LSTA grant).  A second pre-test, by U. North Florida in collaboration with UF is also underway.  To these will added historic newspapers also from microfilm generated by UF with funds from other grants (IMLS and NEH, not reported in Expense sheet; not cost-share per federal regulation.)

- Create Web interface and database 
Systems run by the Florida Center for Library Automation could not be configured to accommodate newspapers.  UF designed and launched new technologies, under Greenstone freeware, that will accommodate newspapers.  
The newspaper tool-kit has not been fully implemented.  This is tentatively scheduled for the summer.  Until then, we may make newspapers available in a more rudimentary (more microfilm reel-like) fashion, i.e., searchable text will be deployed in a phase 2 launch.

- Develop publicity materials to be used by participating newspapers and for distribution to local libraries and schools 
Pending finalization of web interface.

Library/Organization  University of Florida Libraries

Project Name Rewiring Florida’s News

Project Number 05-LSTA-F-13 Grant  Award  $95,000

LSTA OUTCOMES PLAN

Outcomes:

- Public uses technology to get information.
Pending deployment of digitized newspapers in new systems.

Indicators:

- # of hits on newspaper database 
Pending deployment of digitized newspapers in new systems.
Verifying: new systems maintain hit logs.

- Inspection of use logs to determine hits by user category, e.g., .gov, .edu, .com 
Pending deployment of digitized newspapers in new systems.
Verifying: logs can be read to configure user type data and other types of data: e.g., search strings, search sequences, duration of image/text display as an indication of usefulness.

- # responses  to pop-up questionnaire that will be online for first two weeks in September 
Pending deployment of digitized newspapers in new systems.
User surveys both online and in focus groups have been used, so far, to determine the structure of new digital library technologies.  Both online surveys and focus groups will continue to be used at future deployment stages.

- . # electronic publicity packages sent to:

  - newspapers

  - branch public libraries

  - libraries of community colleges

  - public high school libraries 
Pending deployment of digitized newspapers in new systems.

Library/Organization  University of Florida Libraries

Project Name Rewiring Florida’s News

Project Number 05-LSTA-F-13 Grant  Award  $95,000

| 103 Historic Newspaper Titles Imaged To-Date | UF ID |
| --- | --- |
| Alachua advocate (Gainesville) | UF00054870 |
| Ancient city (St. Augustine) | UF00048575 |
| Apalachicola courier (Apalachicola) | UF00048584 |
| Apalachicolian (Apalachicola) | UF00048583 |
| Cedar Key Gulf-Coaster | UF00054176 |
| Columbia Democrat (Alligator) | UF00048743 |
| Columbian (Lake City) | UF00048741 |
| Commercial advertiser (Apalachicola, Fla. : 1843) | UF00048473 |
| Conservator (Ocala) | UF00048640 |
| Cotton states (Micanopy) | UF00023943 |
| Daily advocate (Gainesville) | UF00054635 |
| Daily bee (Gainesville) | UF00054651 |
| Daily Florida citizen | UF00053708 |
| Daily Florida standard (Jacksonville) | UF00053707 |
| Daily item (Ocala) | UF00048730 |
| Daily military review (Jacksonville) | UF00053706 |
| Daily Sun | UF00028299 |
| Daily sun and press (Jacksonville) | UF00048610 |
| De Soto County news (Arcadia) | UF00054175 |
| Dixie (Jacksonville, FL) | UF00048818 |
| East Florida advocate (Jacksonville) | UF00048616 |
| East Florida banner (Ocala) | UF00048737 |
| East Floridian (Fernandina) | UF00054486 |
| Fernandina observer | UF00054481 |
| Florida (Hawkinsville, FL) | UF00049045 |
| Florida Christian advocate | UF00048739 |
| Florida courier (Tallahassee) | UF00048573 |
| Florida democrat and mechanic’s and workingman’s advocate | UF00048637 |
| Florida home companion (Ocala) | UF00048735 |
| Florida index (Lake City) | UF00048742 |
| Florida journal (Apalachicola) [1840-1843] | UF00048580 |
| Florida journal (Apalachicola) [1844] | UF00048581 |
| Florida mirror (Fernandina) | UF00054505 |
| Florida news | UF00054483 |
| Florida weekly record (Gainesville) | UF00054653 |
| Florida republican | UF00028425 |
| Florida ruralist (Interlachen) | UF00049044 |
| Florida semi-tropical news (Ocala) | UF00048736 |
| Florida sentinel (Gainesville) | UF00048669 |
| Florida sentinel bulletin (Tampa) | UF00048668 |
| Florida star (New Smyrna) | UF00048738 |
| Florida State journal (Cedar Key) | UF00054177 |
| Florida sun (Jacksonville, FL) | UF00050169 |
| Florida times-union (Jacksonville, 1883) | UF00053710 |
| Florida union (Jacksonville) | UF00053711 |
| Florida watchman (Tallahassee) | UF00048572 |
| Florida weekly press (St. Augustine) | UF00048574 |
| Gainesville times | UF00054652 |
| Gulf-Coast news (Cedar Key) | UF00054178 |
| Hernando news (Brooksville) | UF00054180 |

Library/Organization  University of Florida Libraries

Project Name Rewiring Florida’s News

Project Number 05-LSTA-F-13 Grant  Award  $95,000

| Jacksonville advocate (Jacksonville, FL) | UF00050170 |
| --- | --- |
| Jacksonville courier | UF00028424 |
| Jacksonville herald (Jacksonville, FL) | UF00050171 |
| Jacksonville standard (Jacksonville, FL) | UF00050172 |
| Jasper News | UF00028306 |
| Kerr City advertiser | UF00050173 |
| Key of the Gulf (Key West) | UF00048587 |
| Key West citizen (Key West) | UF00048666 |
| Key West dispatch (Key West) | UF00048588 |
| Key West enquirer (Key West) | UF00049046 |
| Key West gazette (Key West) | UF00048586 |
| Ledger | UF00054654 |
| Levy Times-Democrat (Bronson) | UF00054174 |
| Live Oak (Pensacola) | UF00048636 |
| Magnolia advertiser (Magnolia) | UF00048624 |
| Marianna courier (Marianna) | UF00048744 |
| Marion free press (Ocala) | UF00048731 |
| Metropolis (Jacksonville, FL) | UF00048819 |
| Miccosukee Everglades news | UF00053712 |
| Military musings | UF00054655 |
| New Capitol (Ocala) | UF00048732 |
| New era (Gainesville) | UF00054656 |
| New era (Key West) | UF00048621 |
| New South (Jacksonville) | UF00048585 |
| News (Fernandina) | UF00054507 |
| News (Sarasota) | UF00048667 |
| News-register (Brooksville) | UF00054181 |
| News-Sun | UF00028423 |
| Ocala argus (Ocala) | UF00048641 |
| Ocala banner (Ocala : 1883) | UF00048734 |
| Peninsula (Fernandina) | UF00048578 |
| Pensacola commercial (Pensacola) [daily] | UF00048638 |
| Pensacola commercial (Pensacola) [weekly, semiweekly] | UF00048664 |
| Polk County record | UF00054480 |
| Quincy sentinel (Quincy) | UF00048628 |
| Quincy times (Quincy) | UF00048576 |
| St. Augustine examiner (St. Augustine) | UF00048642 |
| St. Augustine record (St. Augustine) | UF00048662 |
| Seminole Indian news | UF00053713 |
| South Floridian (Key West) | UF00048665 |
| Southern sun (Ocala) | UF00048733 |
| Star of the west (St. Augustine) | UF00048577 |
| Sunland tribune (Tampa) | UF00048571 |
| Tallahassee sentinel (Tallahassee) | UF00048626 |
| Telegraph | UF00054179 |
| Tri-weekly union (Jacksonville) | UF00048589 |
| Tuskawilla news (Micanopy) | UF00048740 |
| Watchman of the Gulf (Apalachicola) | UF00048579 |
| Weekly Florida citizen (Jacksonville) | UF00053709 |
| Weekly sun and press (Jacksonville) | UF00048590 |
| West Florida times (Pensacola) | UF00048634 |
| Whig banner (Palatka) | UF00048639 |
| El Yara (Key West) | UF00048643 |